## Sheet1
PHASE | TASK | ACTUAL COST | NEGOTIABLE COST | DURATION (WEEKS)
PLANNING & DESIGN | Requirement Analysis and Documentation | 500 |  | 1
| Wireframing and Prototyping | 800 |  | 1
| UI/UX Design | 1200 |  | 2
| Total for Phase 1 | 2500 |  | 2
FRONT-END DEVELOPMENT | Homepage Development | 1000 |  | 2
| Packages Page Development | 800 |  | 1
| Static Content Pages | 600 |  | 1
| Total for Phase 2 | 2400 |  | 3
BACK-END DEVELOPMENT | Database Design and Setup | 1000 |  | 1
| User Authentication System | 1200 |  | 1
| Tutor Profile Management | 1500 |  | 1
| Student Profile Management | 1500 |  | 1
| Total for Phase 3 | 5200 |  | 4
BOOKING & PAYMENT SYSTEM | Booking System Development | 2000 |  | 2
| Payment Gateway Integration | 1800 |  | 2
| Total for Phase 4 | 3800 |  | 4
TESTING & DEPLOYMENT | Quality Assurance Testing | 1200 |  | 1
| Deployment | 800 |  | 1
| Post-Deployment Support | 500 |  | 1
| Total for Phase 5 | 2500 |  | 2
GRAND TOTAL |  | 16400 |  | 15 Weeks